# HSH General Contracting Workflow & Execution Playbook

PURPOSE

This document defines the standard operating workflow for all HSH general contracting projects. It establishes clear sequencing, responsibility expectations, protection standards, and execution gates to ensure consistent, high-quality project delivery.

This playbook is intended for project managers, superintendents, and field leadership and represents the baseline standard for how HSH runs jobs.

--------------------------------------------------

PHASE 1: PROJECT INITIATION, PROCUREMENT & PERMIT SETUP

Starting Point: Closed deal, shovel-ready

1. Finalize Construction Plans

- Confirm plans are fully permit-ready

- Resolve outstanding design, structural, or code issues

- Issue plans for construction (IFC)

2. Permits

- Submit for all required permits

- Track permit approvals and numbers

3. Material Procurement

- Identify all major materials required for the project

- Place orders and confirm lead times

- Secure materials onsite or offsite in alignment with schedule

4. Subcontractor Buy-Out & Scheduling

- Secure all required subcontractors

- Confirm scope, pricing, and sequencing

- Establish tentative start windows

5. Power Coordination

- Obtain work order numbers for temporary and permanent power

- Coordinate meter and service locations

6. Gas Utility Coordination

- Contact gas company

- Schedule site visit after framing for gas line installation

Phase 1 Complete When:

- IFC plans issued

- Permits submitted or approved

- Materials ordered and secured

- Subcontractors bought out and scheduled

- Utilities coordinated

--------------------------------------------------

PHASE 2: SITE WORK & FOUNDATION

1. Utility Verification & Tie-Ins

- Call for utility locates (811)

- Confirm utilities are marked

- Identify water and sewer tie-in locations

2. Foundation Excavation

- Excavate per plans

- Verify depth, layout, and bearing conditions

3. Footer Layout & Drainage

- Frame footers

- Install footer drains

- Confirm sump pump location and drain routing

4. Footer Pours

- Pour perimeter and interior footers

- Schedule and pass inspections

5. Basement Gravel Base

- Cover drainage system

- Bring floor elevation level with footers

6. Foundation Walls

- Install foundation walls

- Confirm all wall openings prior to install

7. Waterproofing & Below-Grade Insulation

- Waterproof all below-grade walls

- Install insulation

8. Backfill

- Backfill with #57 gravel

9. Basement Floor Slab

- Confirm drains and bathroom rough-ins

- Pour slab

Phase 2 Complete When:

- Foundation complete and backfilled

- Basement slab poured

- All inspections passed

--------------------------------------------------

PHASE 3: FRAMING & DRY-IN

1. Framing Readiness

- Framing materials onsite and secured

- IFC plans onsite

- Window and door rough opening information finalized and available

- Foundation inspections passed

2. Wood Framing

- Complete all structural framing per plans

3. Windows & Exterior Doors

- Install immediately after framing to seal structure

4. Blocking Identification & Installation

- Install blocking for cabinets, handrails, grab bars, towel bars, and accessories

5. Garage Opening Temporary Access

- Frame garage opening with plywood

- Install hinged temporary access door

Phase 3 Complete When:

- Framing complete

- Windows and exterior doors installed

- Blocking verified

- Garage temporary access installed

- Framing inspection passed

--------------------------------------------------

PHASE 4: MEP ROUGH-IN & EXTERIOR ENVELOPE

1. Plumbing Rough-In

- Tubs and shower valves onsite prior to start

2. HVAC Rough-In

3. Electrical Rough-In

4. Exterior Coordination for MEP

- Siding and exterior components required for penetrations onsite

5. Roofing & Exterior Envelope

- Roofing, siding, fascia, soffits, gutters installed

6. Insulation

- Install insulation and pass inspection

7. Drywall

- Floors papered before finishing

- In cold months, heat must be operational before drywall begins

8. Garage Door Installation

- Install garage door after drywall finishing

Phase 4 Complete When:

- MEP rough-ins complete and inspected

- Drywall finished

- Building fully dried-in

--------------------------------------------------

PHASE 5: INTERIOR FINISH, FINALS & SITE CLOSE-OUT

1. Prime & Ceiling Finish

- Prime all walls and ceilings

- Final coat on ceilings

2. Carpentry & Cabinet Installation

- Cabinets, trim, interior doors, finish panels installed

- Exterior doors covered and protected immediately

- Exterior door thresholds protected

3. Countertop Measurement

- Measure after cabinets installed

- Typical lead time: approximately 2 weeks

4. Final Paint

- Two coats on trim

- Two coats on walls

5. Final Trade Sequencing

1) Final electrical

2) Flooring

3) Final HVAC

4) Countertops

5) Final plumbing

6. Countertop Protection

- Countertops covered immediately after install

7. Appliances

- Deliver and install appliances

8. Exterior Close-Out

- Final grading and landscaping

- Pour driveways, porches, sidewalks

Phase 5 Complete When:

- All finishes complete

- Utilities active

- Exterior work complete

- Project ready for turnover